## Sheet1
√ | STEP | ACTIVITY | OWNER | MINIMUM TIME REQUIRED | DEPENDENCIES | WORK CONCURRENTLY WITH | TARGET COMPLETION DATE | COMPLETION DATE
| 1 | FCC Order Issued Engages the NANC | FCC
| 2 | NANC Engages the LNPA WG | NANC
| 3 | Determine Need for Immediate LNPA WG Engagement and Scheduling of Meetings. | LNPA WG Co-Chairs
| 4 | LNPA WG Reviews Order Details | LNPA WG
| 5 | Determine Industry Impacts - (check all involved) | LNPA WG
Wireline
Wireless
VoIP
ATIS (OBF, INC, etc.)
NPAC
Vendors
Other (identify)
| 6 | Determine Work Effort Required | LNPA WG
| 7 | Prioitize Work Effort Items Required | LNPA WG
| 8 | Determine Liaisons Required (List Below) | LNPA WG
| 9 | Determine/Establish Subteam(s) to Focus on Specific Work Areas from 5 & 6 above (List Below) | LNPA WG
| 10 | Determine Subteam Leader(s) (List Below) | LNPA WG
| 11 | Establish Project Timeline Based on FCC Order Implementation Date or Direction from the NANC | LNPA WG
| 12 | Engage Other Industry Groups As Necessary (check all involved) | LNPA WG
ATIS (OBF, INC, etc)
NPAC Administrator
NAPM, LLC
PA and/or NANPA Administrator(s)
Service Bureaus and/or Clearing Houses
Local System Vendors (LSMS and SOA)
Other (identify)
| 13 | Develop LNP Process Flow Changes Required | LNPA WG
| 14 | Invoke Change Order Process | LNPA WG
NPAC
SP(s)
Vendor(s)
| 15 | Develop New Industry Processes in Support of Order (check all involved)
LNPA WG
ATIS (OBF, INC, etc)
NPAC Administrator
NAPM, LLC
PA and/or NANPA Administrator(s)
Service Bureaus and/or Clearing Houses
Local System Vendors (LSMS and SOA)
VoIP Providers
Other (identify)
| 16 | LNPA WG Subteam Updates to LNPA WG (TBD in Timeline) | LNPA WG Subteams
| 17 | IndustryParticipants Updates to LNPA WG (TBD in Timeline)
| 18 | Periodic Status Reports to NANC (TBD in Timeline)
| 19 | NANC Change Order Approval | NAPM LLC
| 20 | Pre-Implementation Testing (check all involved)
NPAC
Vendors
Service Providers
Other (identify)
| 21 | NPAC Change Order Implementation | NPAC
Vendors
| 22 | New Process Implementation from 13 & 14 above | Industry
| 23 | Monitor Compliance ???? | LNPA WG
| 24 | Periodic Compliance Status Reports to NANC/FCC (TBD in Timeline) | LNPA WG